## Sheet1
Annex 5 Implementation Timetable: ASCENT GREEN 1,2
Project/Programme Title:
COMPONENTS/ACTIVITIES | Indicative Deliverables (at program level, not project specific) | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7 |  |  |  | Year 8
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1 : ASCENT REAF Project: Regional Debt financing, RBF facilities & Equity Facility for DRE
Activity 1.1 Lending to DRE and Clean Cooking Companies: This activity will expand access to electricity, clean cooking and PUE through the provision of a credit line to lend to (i) eligible private/commercial enterprises legally operating in participating countries or (ii) eligible participating financial institutions (PFIs) in participating countries for on-lending to eligible private/commercial enterprises to finance eligible DRE, clean cooking and PUE products and services. | Loans to DRE and clean cooking companies provided | Year 1 Q1: Inception Report; Year 1 Q2: TDB Onboarding, Pipeline Development, Awareness raising among DRE companies; Year 1 Q4: TDB starts receiving applications from DRE companies; Year 2 Q1: Pipeline Development, Deal processing (TDB Deal teams and Internal committee - ongoing process Y2, Y3, Y4, Y5, Y6, Y7); Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Activity 1.2 Results-Based Financing (RBF) for Frontier Markets: This activity will finance a regional RBF facility, already established by TDF, providing grant funding via RBF and performance-based catalytic grants to DRE companies to support the expansion of DRE systems, clean cooking solutions, and productive uses equipment in unserved and underserved geographic areas of participating countries. | Grants through RBFs to DRE and clean cooking companies provided | Year 1 Q1: Inception Report; Year 1 Q2: TDB Onboarding; Engagement with Governments on priorities, funding gaps and aligning eligibility crieteria; Year 1 Q4: Call for proposals (AFE DRE companies); Year 2 Q1: Subsidy grant agreements signing and milestone payments and periodic calls for proposals with ongoing consultations with Governments (TDB RBF team and Internal committee - ongoing process Y2, Y3, Y4, Y5, Y6, Y7); Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Activity 1.3 Technical Assistance, Tools and Innovations for DRE and Clean Cooking: This activity aims to build the capacity of key stakeholders, including TDB, TDF, the region’s commercial banks and other financial institutions, and DRE companies to play their roles in ASCENT-REAF and to encourage innovations in DRE, clean cooking and PUE market segments. | TA to TDB, TDF, PFIs and DRE and clean cooking companies provided | Year 1 Q1: Inception report; Year 1 Q2: TDB/TDF TA Provider Selection and Onboarding; Year 2 Q1: TA provision to TDB and TDF (rolling through Year 6)
Activity 1.4 Enable capitalization of Zafiri : This activity aims to support DRE companies with financing for sustainable growth, while creating a mechanism for attracting private investment into the DRE sector over time. It will enable capitalization of Mission 300 DRE Permanent Capital Vehicle called ‘Zafiri’. | Equity invested in DRE and clean cooking companies | Year 1 Q1: Inception Report; Year 1 Q2: TDB Onboarding; Year 1 Q4: TDB signs subscription agreement with Zafiri and actively participates in the Zafiri board meetings as an anchor shareholder; Year 2 Q1: Zafiri Investment Manager develops pipeline amd process deals and TDB seats in the board and oversees the operation - ongoing process Y2, Y3, Y4, Y5, Y6, Y7; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Project Monitoring* |  | Year 1 Q1: Inception Report & APR; Year 2 Q1: APR; Year 3 Q1: APR; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Component 2 : ASCENT REAF : Regional De-risking Facilities for DRE
Activity 2.1 Risk-Sharing Facility: This activity tackles challenges for DRE companies in securing local currency debt financing from commercial lenders through i) capitalizing and backstoping the RSF which will enable the regional EE to provide partial credit guarantees (PCGs) to eligible PFIs to expand commercial lending to DRE companies and providing technical assistance for PFIs and institutional strengthening and Implementation Support. | Partial credit guarantees issued TA provided to PFIs | Year 1 Q1: Inception Report; Year 1 Q2: EE Onboarding; Year 1 Q4: Call for applications (AFE PFIs); Year 2 Q1: Pipeline Development, Deal processing (EE Deal teams and Internal committee - ongoing process Y2, Y3, Y4, Y5, Y6, Y7), TA supporting pipeline development, PFI capacity building, and EE due diligence; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Activity 2.2 Carbon Risk Mitigation Facility: This activity will (i) stabilize the carbon market by providing a floor price guarantee for carbon credits generated in the DRE sector; (ii) reduce carbon transaction costs and increase market efficiency by aggregating demand and attracting institutional buyers; and (iii) support a more conducive environment for carbon market participation through policy coordination and harmonization. | Floor price guarantees provided to DRE and clean cooking companies TA provided to key stakeholders (EE, DRE companies, governments) on carbon market transactions | Year 1 Q1: Inception Report; Year 1 Q2: EE Onboarding and selection of a facility manager; Year 1 Q4: Call for applications (AFE DRE companies); Year 2 Q1: Pipeline Development, Deal processing (EE/facility manager deal teams and EE Internal committee - ongoing process Y2, Y3, Y4, Y5, Y6, Y7), TA supporting pipeline development, key stakeholder capacity building, and EE due diligence; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Project Monitoring* |  | Year 1 Q1: Inception Report & APR; Year 2 Q1: APR; Year 3 Q1: APR; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Component 3: Regional Energy Access Acceleration Platform
Activity 3.1 COMESA Regional Energy Access Acceleration Platform: This activity aims to create an enabling environment for the acceleration of electrification and DRE solutions (inclusive of PUE equipment and clean cooking) in the AFE region by providing D-MRV platforms, establishing a Project Preparation Facility, offering advisory services for country governments and providing technical assistance. | D-MRV platforms established Advisory services for country governments provided Project preparation facility to provide support to DRE companies operational and TA to companies being provided | Year 1 Q1: Inception Report; Year 1 Q2: Regional d-MRV platform established. TA Facility Consultant Onboarding, Pipeline development and awareness for DRE companies. Conultations with Governments on Ta priorities. Framework contracts for advisory services in place; Year 1 Q4: First call for proposals (AFE DRE companies for PPF and Governments for Advisory Facility); Year 2 Q1: TA funding approvals.; Year 2 Q2: TA funding approvals. Match successful applications with grants and roster of experts; TA provision. Support to Government in setting up and operationalizing d-MRV at the national level. Periodic calls for propoposal and repeat of activities in Year 2, 3,4,5, 6 and 7; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
Project Monitoring* |  | Year 1 Q1: Inception Report & APR; Year 2 Q1: APR; Year 3 Q1: APR; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Year 7 Q3: Completion Report; Year 8 Q1: Final evaluation
1 The annual allocation of the budget is indicative.
2 The alloction for each of the activities is indicative.
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Yabei Zhang could you help fill in some milestones for the CRMF in this line of the implementation timeline? Reply: @Yabei Zhang I’ve tried to fill this in but would be good if you could take a look. Also will ATIDI also do the carbon floor price guarantees?

## Sheet2
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.
Notes:
According to country FA - closing date of each country is different
As per Rwanda FA - 2 implemeting entities with different reporting timelies.
STP : No annual report mentioned in FAA
Pipeline reporting refers to pipeline projects that would need funding
Name of Country | Closing Date
Burundi | 2029-06-30
STP | 31st Dec 2029
Tanzania | 2028-12-29
Rwanda | 31st Dec 2029
Malawi | 2030-12-31